## Estimate Timelines
Scope | Time Lines | Description scope
OCI project start and Resources onboard | April 4th , 2022 | Resources already identified and will start from Monday onwards.
Create additional Platform admin roles/users |  | Cloud engineer/Architect will be creating OCI Additional admin roles and take control to build rest of the platform.
Requirements gathering | April 8th , 2022 | FPT cloud architect will be proving HLD/LLD design documents and setup platform with all required cloud services.
& Initial high level platform design documentation - Signoff
Dev and internal UAT instance Build
OCI Platform configurations and adjustments | April 15th , 2022 | FPT will be configuring OCI platform as per requirements and try to replicate AS-IS like existing AWS platform
OCI DevOps setup | April 22nd , 2022
Platform Testing and Demo | April 29th , 2022 | FPT will be performing testing and submit test cases for client’s UAT.
Migrations & Platform Switchover. |  | Demo on platform build/features walk through. (Go /no Go decision for Switchover) Demo on platform build/features walk through. (Go /no Go decision for Switchover)
Perform Switchover from April 29th , 2022 onwards

## Estimate Tasks
Scope | Description scope | Sub-task | Description Tasks | Effort (md)
Create additional Platform admin roles/users | Cloud engineer/Architect will be creating OCI Additional admin roles and take control to build rest of the platform. | Define policy for group user roles | Define user, group, policy for Technical Lea, ML, DevOps, Data Architecture, Dev | 3
|  | Create User, gorup and attach policy to group | Create user, group, policy for Technical Lea, ML, DevOps, Data Architecture, Dev on OCI | 1
Requirements gathering & Initial high level platform design documentation - Signoff & Initial high level platform design documentation - Signoff | FPT cloud architect will be proving HLD/LLD design documents and setup platform with all required cloud services. | Design CICD workflow | Design CI, CD, CICD workflow for FE, BE | 2
|  | Design OCI Architecture | Design architecture use for project on OCI | 3
|  | Create Network resource | Create resource Network ( VCN, Subnet, Security rules, nat gateway, intenet gateway, ..) | 2
|  | Create Compute resource | Create compute, volume, network interface, security group for compute | 2 | Tuấn
|  | Create LoadBlance resource | Create Load Blancing | 1 | Tuấn
|  | Create Database resource | Create mySQL database and setup connect from internet to Database | 2
|  | Set up Code Repository resource | Setup DevOps project and Create repository for FE, BE, ML | 1 | Tuấn
|  | Set up Container Registry resource | Create Container Registry to store images for BE, FE | 1 | Tuấn
|  | Set up Vm resource for backend and frontend | Install Docker on Compute and set up connect with Container Regsitry | 2 | A Biên
OCI Platform configurations and adjustments | FPT will be configuring OCI platform as per requirements and try to replicate AS-IS like existing AWS platform | Config and deploy backend and frontend environment | Deploy FE and BE into Docker application compute | 3 | Tuấn
|  | Migrate Code repository from AWS to OCI | Migrate source code and commit BE, FE from AWS to OCI | 2 | Tuấn
|  | Migrate Data on RDS AWS to OCI mySQL | Migrate database from AWS to OCI | 3 | Tuấn
|  | Migrate Dev enviroment from AWS to OCI | MigrateFE, BE for Dev from AWS to OCI | 5 | Tuấn
|  | Migrate Test enviroment from AWS to OCI | MigrateFE, BE for Test from AWS to OCI | 5 | Tuấn
|  | Migrate Stag enviroment from AWS to OCI | MigrateFE, BE for Stag from AWS to OCI | 5 | Tuấn
|  | Create API GateWay for backend | Create API Gateway and attach with BE | 3 | A Biên, Tuấn
|  | Config Load balancing for frontend. | Attach Compute FE with Load Balance | 1 | A Biên, Tuấn
OCI DevOps setup | Set up DevOps environment. Config CICD for FE & BE | Install Jenkins server to CI | Install and config Jenkins application | 2 | A Biên
|  | Install SonarQube for scan source code | Install and config Sonar application | 2 | A Biên
|  | Setup CI pipline for featrue branch | Set up CI pipeline on Jenkins to CI ( build UT, scan sonar) for BE, FE | 4 | A Biên
|  | Setup CICD for FE focus (2day) each environment | Set up CICD pipeline on Jenkins to CICD ( build UT, scan sonar, build image, deploy) for FE | 3 | A Biên
|  | Setup CICD for BE focus (2day) each environment | Set up CICD pipeline on Jenkins to CICD ( build UT, scan sonar, build image, deploy) for FE | 3 | A Biên
Platform Testing and Demo Migrations & Platform Switchover. | FPT will be performing testing and submit test cases for client’s UAT. Demo on platform build/features walk through. (Go /no Go decision for Switchover) Perform Switchover from April 29th , 2022 onwards | Inform Dev check function and Data on Dev environment
Inform Tester check function and Data on Test, Stag environment
|  | Support fix issues when migrate. | Fix issuse when Tester, Dev check new environment on OCI | 5
|  | Support Build CICD Test environment | Set up ci, CICD pipeline on Jenkins to CICD ( build UT, scan sonar, build image, deploy) for FE, BE on Test environment | 10
|  | Support Build CICD Staging environment | Set up ci, CICD pipeline on Jenkins to CICD ( build UT, scan sonar, build image, deploy) for FE, BE on Stag environment | 10
|  | Support Build CICD Product environment | Set up ci, CICD pipeline on Jenkins to CICD ( build UT, scan sonar, build image, deploy) for FE, BE on Product environment | 10
|  |  | Total | 96