## Checklist
No | Task | Description | Estimate | PIC | Status
1 | Create Network resource for Prod | Create resource Network ( VCN, Subnet, Security rules, nat gateway, intenet gateway, ..) | 2 | Tuấn | Done
2 | Create Compute resource for Prod | Create compute, volume, network interface, security group for compute | 2 | Tuấn | Done
3 | Create LoadBlance resource for Prod | Create Load Blancing | 1 | Tuấn | Done
4 | Create Database resource for Prod | Create mySQL database and setup connect from internet to Database | 2 | Tuấn | Done
5 | Set up Vm resource for backend and frontend | Install Docker on Compute and set up connect with Container Regsitry | 2 | A Biên | Done
6 | Config and deploy backend and frontend environment | Deploy FE and BE into Docker application compute | 3 | Tuấn | Done
7 | Config Load balancing for frontend and backend | Attach Compute FE with Load Balance | 1 | A Biên, Tuấn | Done
8 | Setup peering network from Jenkins to Prod Application VM | Setup peering network from Jenkins to Prod Application VM | 2 | A Biên, Tuấn | Done
9 | Setup CICD pipline for master branch | Set up CI pipeline on Jenkins to CI ( build UT, scan sonar) for BE, FE | 4 | A Biên | Done
ENV | Task | Description | Estimate | PIC | Status | Remark
Prod | Create and install OKE ( Public LB) |  | 2 |  | Done
| Write yaml file service for FE | Helm chart | 1 |  | Done
| Write yaml file service for BE | Helm chart | 1 |  | Done
| Write yaml file service for BE- tracking | Helm chart | 1 |  | In-progress
| Write yaml file service for RabbitMQ ( OKE operator) | RabbitMQ Cluster Kubernetes Operator Quickstart — RabbitMQ | 3 |  | Done
| Install VM and config for Cassandra |  | 3 |  | Done
| Install VM and config for Solr |  | 3 |  | Done
| Write yaml file service for ML server | Helm chart | 1 |  | To Do
| Write yaml file service for ETL server | Helm chart | 1 |  | Done
| Install ArgoCd | Use for Deploy and rollback (https://developer.oracle.com/tutorials/deploying-the-argo-project-on-oke/) | 3 |  | Done
| Setup Access Rule for Ingress Controller | create service account and permission role for Ingress use for expose svc for FE, BE,… | 2 |  | Done
| Install Ingress Controller and config rules path. | Ingress use for expose svc for FE, BE,… (https://github.com/kubernetes/ingress-nginx/tree/main/charts/ingress-nginx) | 3 |  | In-progress
| Create repo helm chart for deploy on OKE | helm chart repo | 3
Done
| Argo Image Updator (Option ) |  | 3 |  | Done
| Peering network with OKE dev |  | 1 |  |  | Cheking connection
| PVC for RabbitMQ | pvc khi create rồi , Nhung prc khi tạo lại thì ntn | 2
| Config RabbitMQ for BE connect | Work with Dev team | 1 |  | Done
| Setup ML server for Test |  | 0.5 |  | Done
| CICD for ML on Test env |  | 1 |  | Done
| Setup ML server for Staging |  | 0.75 |  | Done
| CICD for ML on Staging env |  | 1.5
Re Build Docker Image for BE (Dockerfile )
Check list verify Status | OKE Authenticarion with Registry | Service account was locked => can not pull images from Oracle Registry |  |  | In-progress
| ArgoCD Authentication with OKE Cluster | Update password for ArgoCD => Update authentication between ArgoCD and OKE Cluster |  |  | Done
| Pipeline build image FE for Prod | Setup builder images for FE |  |  | To Do
| Pipeline build image BE for Prod | Setup builder images for FE |  |  | To Do
| Pipeline build image Tracking for Prod | Setup builder images for FE |  |  | To Do

## Dev-Staging
Dev | Create and install OKE (public LB)
Write yaml file service for FE
Write yaml file service for BE
Write yaml file service for BE- tracking
Write yaml file service for RabbitMQ
| Install VM and config for Cassandra (docker) | Now running on Docker
| Install VM and config for Solr | Now running on Docker
Write yaml file service for ML server
| Install ArgoCd | Use for Deploy and rollback (https://developer.oracle.com/tutorials/deploying-the-argo-project-on-oke/)
| Setup Access Rule for Ingress Controller | Option
| Install Ingress Controller and config rules path. | Option
Create repo helm chart for deploy on OKE
Deploy helm chart and check issue
Config repository configuration on argoCD
Argo Image Updator (Option )
Staging | Create and install OKE ( Public LB) |  | 2
| Create VCN on OCI |  | 1
| Write yaml file service for FE | Helm chart | 1
| Write yaml file service for BE | Helm chart | 1
| Write yaml file service for BE- tracking | Helm chart | 1
| Write yaml file service for RabbitMQ ( OKE operator) | RabbitMQ Cluster Kubernetes Operator Quickstart — RabbitMQ | 3
| Install VM and config for Cassandra |  | 3
| Install VM and config for Solr |  | 3
| Write yaml file service for ML server | Helm chart | 1
| Install ArgoCd | Use for Deploy and rollback (https://developer.oracle.com/tutorials/deploying-the-argo-project-on-oke/) | 3
| Setup Access Rule for Ingress Controller | create service account and permission role for Ingress use for expose svc for FE, BE,… | 2
| Install Ingress Controller and config rules path. | Ingress use for expose svc for FE, BE,… (https://github.com/kubernetes/ingress-nginx/tree/main/charts/ingress-nginx) | 3
| Create repo helm chart for deploy on OKE | helm chart repo | 3
| Argo Image Updator (Option ) |  | 3
| Peering network with OKE dev |  | 1
| PVC for RabbitMQ | pvc khi create rồi , Nhung prc khi tạo lại thì ntn | 2
| Config RabbitMQ for BE connect | Work with Dev team | 1
| Setup ML server for Test |  | 0.5
| CICD for ML on Test env |  | 1
| Setup ML server for Staging |  | 0.75
| CICD for ML on Staging env |  | 1.5
Re Build Docker Image for BE (Dockerfile )