## Estimate Time
Environment | Dev,Test
| Name | Description | Estimate times | Date
| Document for Architecture - Dev, Test, staging | High level Architecture for Dev, Test, Staging |  | 2022-11-03
| Document login Jenkins , Sonar | Document for access to Jenkins, Sonar by tennal jump host | 1.5 | 2022-11-04
| Document Create VM and install application on VM | Document for Create VM and install requirement and application | 1 | 2022-11-05
| Document for setup agent for Jenkins ( to deploy ) | Setup Jenkins agent and use that agent to deploy application | 1 | 2022-11-05
| Document Setup Jenkins pipeline to CICD for backend - dev | Guildeline create an pipeline CICD for example backend service | 1 | 2022-11-08
| Document setup trigger when commit PR on Oracle. | Guideline setup trigger when have a PR from Oracle repo auto trigger to deploy application | 1 | 2022-11-08
| Document for setup LB for FE, BE | Setup LoadBalancer for services example Backend services | 1.5 | 2022-11-09
Environment | Prod
| Name | Description |  | Date
| Document for Architecture- Prod | High level Architecture for Prod |  | 2022-11-03
| Document Create OKE | Document for Create OKE | 1.5 | 2022-11-10
| Document for config build image on Oracle | Setup Build image when have PR and push into Oracle registry | 1.5 | 2022-11-10
| Document for access ArgoCD & connect OKE | Document for access to ArgoCD and connection between OKE with ArgoCD | 1 | 2022-11-11
| Document for deploy by ArgoCD and helm | Guideline Deploy application for production by Helm, ArgoCD | 1.5 | 2022-11-14
| Total and Question meeting |  | 1 | 2022-11-15